## HWTE Team
TEAM | NPI SW |  |  |  | Risk
On-Going
Closed
| Category | No. | Items | Description | Status | CP | DRI
| Manpower | 1 | Attendance, Working NS/DS | Attend: 3x/3T (All in DS) | On-Going | 2024-07-15 | Eden
|  | 2 | OT plan | 2x/ 3T: 67% | On-Going | 2024-07-15 | Eden
|  | 3 | Resources matrix | 2024Y CQ3 Vendors and CM name list locked down | Closed | / | Vincent
| Web MAC NPI | 3 | MTS | - Deploy on local & Re-make SOP (Done) - Re-deploy MTS on server 10.221.132.13 : Move & Install libs to server (Done) Config uWSGI & nginx (Done) Build success : http://10.221.132.13/en/mts/login/ - Tracking update new features (On-going) | On-Going | 2024-08-31 | Eden/Dustin
|  | 4 | Academy | - Station ID and Build stage: Done | Closed | 2024-09-01 | Eden
|  |  |  | - Deploy on local & Re-make SOP (Done) - Re-deploy on server 10.221.132.13 : + Move & Install libs to server (On-going) +Config uWSGI & nginx (On-going) - Tracking update new features (On-going) | On-Going | 2024-08-31 | Eden/Frenkie
Closed
On-Going
Closed
Closed
On-Going
|  | 5 | SWAT | - Jmet server setup confirmation - FDR server setup - Fusing server setup - Provisioning readiness - Marina server setup | Closed | 2024-09-08 | Eden
|  |  |  | - Deploy on local & Re-make SOP (Done) - Re-deploy on server 10.221.132.13 : + Move & Install libs to server (On-going) + Config uWSGI & nginx (On-going) - Tracking update new features (On-going) | On-Going | 2024-08-31 | Eden/Frenkie
On-Going
On-Going
|  | 6 | ATS | - Deploy on local & Re-make SOP (Done) - Re-deploy on server 10.221.132.13 : + Move & Install libs to server (On-going) + Config uWSGI & nginx (On-going) - Tracking update new features (On-going) | On-Going | 2024-08-31 | Eden/Dustin
|  | 8 | Transtation System | - Build a successful translation application with basic interface and functions. - Can support translation of languages ​​such as English, Chinese, Vietnamese. - Supports transcription for Chinese and English. - User feedback feature helps developers understand issues that need to be upgraded or changed. - Deployed on server 10.221.156.90:8002 | On-Going | 2024-08-31 | Frenkie
On-Going
On-Going
|  | 9 | Chat System | - Build an internal chat application for VN-NPI members with usable interface and basic features. - Search and make friends function to manage connections with members in VN-NPI. - The fixed account login feature is provided to ensure identity and security for the application. - Real-time messaging features combined with notifications give users the same feeling as using regular social networks. - Deployed on server (maintainance) - Feature to send files via chat for convenience in exchanging work. - A number of other features are being completed and continue to develop other features to meet user needs. | On-Going | 2024-08-31 | Frenkie
On-Going
On-Going
On-Going
| Others | 14 | / | /

## DRI List
Team | Lead | PM
RF | Robert/Brian/Johnny | Hana/Joy/Alee
EE + Component | Leo/Javis/Dylan/Max | Megane/Sarah
TDE | Zed/Eden/Jason | Sammy/Kendy
HWTE | Vincent | Swan/Hera

## Sheet1
HWTE Overtime | [7 empty] | Reason for overtime | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-06 | 2024-07-07 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31
HW-TE | V0515938 | Nguyễn Văn Dân | Vicent Ruan | 阮文民 | Barbie | Day shift | 0328380756 | DRI FATP line barbie FBU (Setup/debug/calibration/audit/GRR/Report/TIL) | 2024-07-01: 1.5; 2024-07-05: 2; 2024-07-09: 2; 2024-07-11: 2; 2024-07-15: 2; 2024-07-16: 2; 2024-07-17: 2; 2024-07-18: 2; 2024-07-19: 2; 2024-07-20: 0; 2024-07-22: 2; 2024-07-23: 2; 2024-07-24: 2; 2024-07-25: 2; 2024-07-26: 2; 2024-07-29: 2; 2024-07-30: 2; 2024-07-31: 0
| V0518294 | Nguyễn Văn Tiến | Alex | 阮文進 |  | Day shift | 0964880815 | DRI FATP line barbie FBU SA-FACT/QT3/QT4/SS station (Setup/debug/calibration/audit/GRR/Report/TIL) | 2024-07-02: 1.5; 2024-07-04: 2; 2024-07-08: 2; 2024-07-13: 2; 2024-07-15: 2; 2024-07-16: 2; 2024-07-17: 2; 2024-07-18: 2; 2024-07-20: 2; 2024-07-22: 2; 2024-07-23: 2; 2024-07-24: 2; 2024-07-25: 2; 2024-07-26: 2; 2024-07-27: 2; 2024-07-29: 2; 2024-07-30: 2; 2024-07-31: 2
| V0515897 | Lương Văn Vương | Alistar Liang | 梁文王 |  | Day shift | 0345467577 | DRI FATP line barbie FBU TFT-QT/Camera-QT/Display/CR-QT1/CR-QT2 station (Setup/debug/calibration/audit/GRR/Report/TIL) | 2024-07-02: 1.5; 2024-07-08: 2; 2024-07-10: 2; 2024-07-13: 2; 2024-07-15: 2; 2024-07-16: 2; 2024-07-17: 2; 2024-07-19: 2; 2024-07-20: 2; 2024-07-22: 2; 2024-07-23: 2; 2024-07-24: 2; 2024-07-25: 2; 2024-07-26: 2; 2024-07-27: 2; 2024-07-29: 2; 2024-07-30: 2; 2024-07-31: 2
| V0517865 | Trần Văn Nhật | Lee | 陳文日 |  | Day shift | 0338126182 | DRI FATP line barbie FBU TP Force/Actuator/Mesa/USBC/CBT station (Setup/debug/calibration/audit/GRR/Report/TIL) | 2024-07-02: 1.5; 2024-07-06: 2; 2024-07-10: 2; 2024-07-13: 2; 2024-07-15: 2; 2024-07-16: 2; 2024-07-17: 2; 2024-07-19: 2; 2024-07-20: 2; 2024-07-22: 2; 2024-07-23: 2; 2024-07-24: 2; 2024-07-25: 2; 2024-07-26: 2; 2024-07-27: 2; 2024-07-29: 2; 2024-07-30: 2; 2024-07-31: 2
| V2106806 | Nguyễn Văn Dương | Roder | 阮文陽 |  | Day shift | 0961979928 | DRI FATP line barbie FBU TFT-QT/Camera-QT/Display/CR-QT1/CR-QT2 station (Setup/debug/calibration/audit/GRR/Report/TIL) | 2024-07-03: 1.5; 2024-07-06: 2; 2024-07-08: 2; 2024-07-11: 2; 2024-07-15: 2; 2024-07-17: 2; 2024-07-18: 2; 2024-07-19: 2; 2024-07-20: 2; 2024-07-22: 2; 2024-07-23: 2; 2024-07-24: 2; 2024-07-25: 2; 2024-07-26: 2; 2024-07-27: 2; 2024-07-29: 2; 2024-07-30: 2; 2024-07-31: 2
| V2112654 | Nguyễn Trọng Đại | Kai | 阮仲代 |  | Day shift | 0393101368 | DRI FATP line barbie FBU SWDL/QT0/KBT/ALS station (Setup/debug/calibration/audit/GRR/Report/TIL) | 2024-07-03: 1.5; 2024-07-06: 2; 2024-07-09: 2; 2024-07-11: 2; 2024-07-15: 2; 2024-07-16: 2; 2024-07-18: 2; 2024-07-19: 2; 2024-07-20: 2; 2024-07-22: 2; 2024-07-23: 2; 2024-07-24: 2; 2024-07-25: 2; 2024-07-26: 2; 2024-07-27: 2; 2024-07-29: 2; 2024-07-30: 2; 2024-07-31: 1.5
| V0518293 | Trương Hồng Nhật | James | 張紅日 |  | Day shift | 0972864718 | DRI FATP line barbie FBU TP Force/Actuator/Mesa/USBC/CBT station (Setup/debug/calibration/audit/GRR/Report/TIL) | 2024-07-03: 1.5; 2024-07-08: 2; 2024-07-11: 2; 2024-07-13: 2; 2024-07-15: 2; 2024-07-17: 2; 2024-07-18: 2; 2024-07-19: 2; 2024-07-20: 2; 2024-07-22: 2; 2024-07-23: 2; 2024-07-24: 2; 2024-07-25: 2; 2024-07-26: 2; 2024-07-27: 2; 2024-07-29: 2; 2024-07-30: 2; 2024-07-31: 2
| V0517211 | Nguyễn Việt Anh | Ronaldo | 阮越英 |  | Day shift | 0961069950 | DRI FATP line barbie FBU FACT/Color cal/DVI/SWReflash station (Setup/debug/calibration/audit/GRR/Report/TIL) | 1.5 |  |  |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 0 | 2 | 2 | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2
| V2113325 | Vũ Minh Quang | Rock | 武明光 |  | Day shift | 0346524578 | DRI FATP line barbie FBU SA-FACT/QT3/QT4/SS station (Setup/debug/calibration/audit/GRR/Report/TIL) | 2024-07-04: 2; 2024-07-08: 2; 2024-07-10: 2; 2024-07-11: 2; 2024-07-15: 2; 2024-07-16: 2; 2024-07-18: 2; 2024-07-19: 2; 2024-07-20: 2; 2024-07-22: 2; 2024-07-23: 2; 2024-07-24: 2; 2024-07-25: 2; 2024-07-26: 2; 2024-07-27: 2; 2024-07-29: 2; 2024-07-30: 2; 2024-07-31: 2
| V0516250 | Trần Xuân Sang | Juns | 陳春貴 |  | Day shift | 0822618897 | DRI FATP line barbie FBU SWDL/QT0/KBT/ALS station (Setup/debug/calibration/audit/GRR/Report/TIL) | 1.5 |  |  |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 0 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2
| V0516287 | Trần Đức Viên | Candy | 陳德園 |  | Day shift | 0964377159 | DRI FATP line barbie FBU FACT/Color cal/DVI/SWReflash station (Setup/debug/calibration/audit/GRR/Report/TIL) | 2024-07-04: 2; 2024-07-10: 2; 2024-07-11: 2; 2024-07-13: 2; 2024-07-15: 2; 2024-07-16: 2; 2024-07-18: 2; 2024-07-19: 2; 2024-07-20: 2; 2024-07-22: 2; 2024-07-23: 2; 2024-07-24: 2; 2024-07-25: 2; 2024-07-26: 2; 2024-07-27: 2; 2024-07-29: 2; 2024-07-30: 2; 2024-07-31: 2
TDL | V2102551 | Nguyễn Thị Hảo | Hera | 阮氏好 |  | Day shift | 0965955880 | Update Barbie TIL and FBU report | 1.5 | 0 | 2 | 0 | 0 | 0 |  | 0 | 2 | 2 | 2 | 0 | 2 |  | 1 | 2 | 1 | 2 | 1 | 2 |  | 1 | 2 | 1 | 2 | 1 | 2 |  | 1 | 2 | 1
| V0517747 | Hoàng Thị Nga | Swan | 黃氏娥 |  | Day shift | 09622716195 |  | 1.5 | 2 | 0 | 2 | 2 | 0 |  | 2 | 2 | 2 | 2 | 0 | 2 |  | 0 | 2 | 0 | 2 | 0 | 2 |  | 2 | 2 | 0 | 2 | 0 | 2 |  | 2 | 2 | 0
| V2113327 | Nguyễn Quang Hiển | Jack | 阮光顯 |  | Day shift | 0335238795 |  | 0 | 0 | 0 | 2 | 2 | 2 |  | 2 | 2 | 0 | 2 | 2 | 0 |  | 2 | 2 | 0 | 2 | 0 | 2 |  | 0 | 2 | 0 | 2 | 2 | 2 |  | 2 | 2 | 2